## Requirement Traceability Matrix
Req. ID | Requirement Description | Manual Test Case ID | Automation ID (Playwright) | API Request ID (Postman) | Status | Linked Defect (Jira)
REQ-01 | User Authentication: System must allow secure login/logout with error handling. | TC-01, 02, 03, 04, 05 | TC-AUTO-05, 06 | TC-API-07 | PASS | None
REQ-02 | Product Discovery: Users must be able to search products via keyword (e.g. Hammer). | TC-06, 07 | TC-AUTO-07, 08 | TC-API-02 | PASS | None
REQ-03 | Interactive UI: Primary buttons must trigger a hover effect. | TC-08 | TC-AUTO-02, 03 | N/A | PASS | None
REQ-04 | Registration Flow: Users must receive confirmation after account creation. | N/A | N/A | N/A | FAIL | TQP-2
REQ-05 | Product Filtering: System must filter results based on price range slider. | TC-10 | N/A | N/A | FAIL | TQP-1
REQ-06 | Cart Management: Users must be able to add items and see updated badge counts. | TC-12, 13, 14, 15 | TC-AUTO-09, 10 | N/A | PASS | None
REQ-07 | Backend Integrity: Data for brands and categories must be accessible via JSON. | N/A | N/A | TC-API-03, 04, 08 | PASS | None
REQ-08 | Security & Logic: Prevention of checkout bypass and negative quantities. | N/A | N/A | N/A | FAIL | TQP-4, TQP-6 (Simulated)